## Dashboard
FutureNest 30-Day Validation Dashboard
Start date | 2026-08-25 |  | End date | 2026-09-23 |  | Website | future.lumicore-labs.com
Overall Progress
Total tasks |  | Completed |  | Remaining |  | Completion %
Progress by Day
Day | Date | Focus | Total | Done | Remaining | Progress
1 | 2026-08-25 | Create the Repository
2 | 2026-08-26 | DNS and VPS Preparation
3 | 2026-08-27 | First Deployment
4 | 2026-08-28 | MVP Scope and Site Skeleton
5 | 2026-08-29 | Affiliate Research and Applications
6 | 2026-08-30 | Tracking Design
7 | 2026-08-31 | Week 1 Review
8 | 2026-09-01 | Homepage
9 | 2026-09-02 | Article One
10 | 2026-09-03 | Article Two
11 | 2026-09-04 | Inspiration Article
12 | 2026-09-05 | Legal and SEO Basics
13 | 2026-09-06 | Local QA and Deploy
14 | 2026-09-07 | Week 2 Review
15 | 2026-09-08 | Pin Batch One
16 | 2026-09-09 | Pin Batch Two
17 | 2026-09-10 | Pin Batch Three
18 | 2026-09-11 | Publish and Schedule
19 | 2026-09-12 | First Measurement Check
20 | 2026-09-13 | Content and Funnel Review
21 | 2026-09-14 | Week 3 Review
22 | 2026-09-15 | Affiliate Follow-up
23 | 2026-09-16 | Analytics Quality Review
24 | 2026-09-17 | Conversion Improvement
25 | 2026-09-18 | Revenue and Economics Review
26 | 2026-09-19 | Audience and Content Decision
27 | 2026-09-20 | Final Data Capture
28 | 2026-09-21 | Draft the Decision
29 | 2026-09-22 | Final Review
30 | 2026-09-23 | Close the Experiment
Progress by Priority
Priority | Total | Done | Remaining | Progress
Must do
Should do
Optional

## Tasks
Day | Date | Focus | Priority | Task | Done | Notes
1 | 2026-08-25 | Create the Repository | Must do | Create a future-nest folder inside the current workspace. | ☐
1 | 2026-08-25 | Create the Repository | Must do | Initialize future-nest as a separate Git repository. | ☐
1 | 2026-08-25 | Create the Repository | Must do | Create the Nuxt project using the current stable Nuxt setup. | ☐
1 | 2026-08-25 | Create the Repository | Must do | Confirm the project runs locally. | ☐
1 | 2026-08-25 | Create the Repository | Must do | Add a README with the project purpose and deployment target. | ☐
1 | 2026-08-25 | Create the Repository | Must do | Add .env.example and confirm secrets are ignored. | ☐
1 | 2026-08-25 | Create the Repository | Should do | Create folders for pages, content, data, assets, and components. | ☐
1 | 2026-08-25 | Create the Repository | Should do | Add a simple homepage placeholder and make the first local commit. | ☐
1 | 2026-08-25 | Create the Repository | Optional | Create the remote repository and push the initial commit. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Must do | Add the future A record for lumicore-labs.com pointing to the VPS IP. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Must do | Verify DNS with nslookup. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Must do | Create /var/www/future-nest on the VPS. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Must do | Clone the separate repository into the VPS directory. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Must do | Confirm the VPS Node.js version supports the Nuxt project. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Should do | Record DNS and VPS details in a private note. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Should do | Confirm the repository branch used for deployment. | ☐
2 | 2026-08-26 | DNS and VPS Preparation | Optional | Perform the first VPS-side install and generation. | ☐
3 | 2026-08-27 | First Deployment | Must do | Generate the Nuxt static output. | ☐
3 | 2026-08-27 | First Deployment | Must do | Configure Nginx for future.lumicore-labs.com. | ☐
3 | 2026-08-27 | First Deployment | Must do | Confirm sudo nginx -t passes. | ☐
3 | 2026-08-27 | First Deployment | Must do | Reload Nginx and open the site. | ☐
3 | 2026-08-27 | First Deployment | Must do | Install or configure HTTPS with Certbot and confirm the HTTPS page loads. | ☐
3 | 2026-08-27 | First Deployment | Should do | Test direct loading of the homepage URL and check browser and Nginx errors. | ☐
3 | 2026-08-27 | First Deployment | Optional | Create and test the deployment script. | ☐
4 | 2026-08-28 | MVP Scope and Site Skeleton | Must do | Add the homepage structure. | ☐
4 | 2026-08-28 | MVP Scope and Site Skeleton | Must do | Add the /off-grid category page or equivalent. | ☐
4 | 2026-08-28 | MVP Scope and Site Skeleton | Must do | Add article route structure. | ☐
4 | 2026-08-28 | MVP Scope and Site Skeleton | Must do | Add a reusable product-card component placeholder. | ☐
4 | 2026-08-28 | MVP Scope and Site Skeleton | Must do | Add navigation and footer. | ☐
4 | 2026-08-28 | MVP Scope and Site Skeleton | Should do | Add a responsive layout and basic metadata. | ☐
4 | 2026-08-28 | MVP Scope and Site Skeleton | Optional | Add a simple visual identity using existing project assets. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Must do | Check Impact publisher requirements and signup flow. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Must do | Check Awin publisher requirements and signup flow. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Must do | Check at least three relevant direct merchant programs. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Must do | Record Sri Lanka eligibility, payout, tax, and traffic-source rules. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Must do | Submit applications where requirements are clear and acceptable. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Should do | Record application dates and confirmation emails. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Should do | Identify five solar, smart-home, or compact-home products. | ☐
5 | 2026-08-29 | Affiliate Research and Applications | Optional | Contact one relevant merchant directly. | ☐
6 | 2026-08-30 | Tracking Design | Must do | Create or select a free Google Analytics 4 property. | ☐
6 | 2026-08-30 | Tracking Design | Must do | Record the measurement ID privately. | ☐
6 | 2026-08-30 | Tracking Design | Must do | Add analytics configuration without committing secrets. | ☐
6 | 2026-08-30 | Tracking Design | Must do | Define page_view, article_view, product_click, and affiliate_redirect events. | ☐
6 | 2026-08-30 | Tracking Design | Must do | Define Pinterest UTM values from the event-tracking checklist. | ☐
6 | 2026-08-30 | Tracking Design | Should do | Add a product-click redirect route if the static architecture supports it. | ☐
6 | 2026-08-30 | Tracking Design | Should do | Run a test visit locally. | ☐
6 | 2026-08-30 | Tracking Design | Optional | Add a lightweight first-party event log only if it needs no database. | ☐
7 | 2026-08-31 | Week 1 Review | Must do | Confirm subdomain, HTTPS, repository, and deployment path. | ☐
7 | 2026-08-31 | Week 1 Review | Must do | Update the affiliate tracker. | ☐
7 | 2026-08-31 | Week 1 Review | Must do | Complete the event-tracking checklist. | ☐
7 | 2026-08-31 | Week 1 Review | Must do | Record blockers and next actions. | ☐
7 | 2026-08-31 | Week 1 Review | Must do | Commit and push the working project state. | ☐
7 | 2026-08-31 | Week 1 Review | Should do | Write three decisions made this week and confirm the three initial article topics. | ☐
7 | 2026-08-31 | Week 1 Review | Optional | Save a baseline screenshot. | ☐
8 | 2026-09-01 | Homepage | Must do | Replace the placeholder homepage. | ☐
8 | 2026-09-01 | Homepage | Must do | Add a clear Future Living value proposition. | ☐
8 | 2026-09-01 | Homepage | Must do | Add links to the first category and articles. | ☐
8 | 2026-09-01 | Homepage | Must do | Add affiliate disclosure access from the footer. | ☐
8 | 2026-09-01 | Homepage | Should do | Add Open Graph metadata and test mobile layout. | ☐
8 | 2026-09-01 | Homepage | Optional | Add one featured-content section. | ☐
9 | 2026-09-02 | Article One | Must do | Complete the article brief. | ☐
9 | 2026-09-02 | Article One | Must do | Research and source each product claim. | ☐
9 | 2026-09-02 | Article One | Must do | Write 10 Off-grid Gadgets You Can Actually Buy. | ☐
9 | 2026-09-02 | Article One | Must do | Add product cards with verified links or clearly marked pending links. | ☐
9 | 2026-09-02 | Article One | Must do | Add disclosure and limitations. | ☐
9 | 2026-09-02 | Article One | Should do | Add internal links and inspect the generated output. | ☐
9 | 2026-09-02 | Article One | Optional | Prepare three Pin concepts. | ☐
10 | 2026-09-03 | Article Two | Must do | Complete the article brief. | ☐
10 | 2026-09-03 | Article Two | Must do | Write 7 Solar-powered Home Upgrades Worth Comparing. | ☐
10 | 2026-09-03 | Article Two | Must do | Source energy and product claims. | ☐
10 | 2026-09-03 | Article Two | Must do | Add comparison criteria and limitations. | ☐
10 | 2026-09-03 | Article Two | Must do | Add product links only where the affiliate path is verified or clearly labeled. | ☐
10 | 2026-09-03 | Article Two | Should do | Add SEO metadata and internal links. | ☐
10 | 2026-09-03 | Article Two | Optional | Prepare three Pin concepts. | ☐
11 | 2026-09-04 | Inspiration Article | Must do | Write 12 Tiny-home Technologies That Make Small Spaces Work. | ☐
11 | 2026-09-04 | Inspiration Article | Must do | Focus on practical reader usefulness. | ☐
11 | 2026-09-04 | Inspiration Article | Must do | Link naturally to relevant products without making every section a sales pitch. | ☐
11 | 2026-09-04 | Inspiration Article | Should do | Add a related-content section and check reading flow on mobile. | ☐
11 | 2026-09-04 | Inspiration Article | Optional | Add one original diagram or comparison table. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Must do | Add privacy page. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Must do | Add contact page using dev.mg4@gmail.com if needed. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Must do | Add affiliate disclosure page or visible disclosure text. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Must do | Add sitemap and robots file. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Must do | Check canonical URLs and page titles. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Should do | Review image licenses and alt text. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Should do | Remove unverified price or commission claims. | ☐
12 | 2026-09-05 | Legal and SEO Basics | Optional | Set up Google Search Console. | ☐
13 | 2026-09-06 | Local QA and Deploy | Must do | Test every navigation link and article URL. | ☐
13 | 2026-09-06 | Local QA and Deploy | Must do | Test product links and tracking events. | ☐
13 | 2026-09-06 | Local QA and Deploy | Must do | Generate the production build. | ☐
13 | 2026-09-06 | Local QA and Deploy | Must do | Deploy through the separate Git repository. | ☐
13 | 2026-09-06 | Local QA and Deploy | Must do | Verify HTTPS and mobile layout. | ☐
13 | 2026-09-06 | Local QA and Deploy | Should do | Check Nginx logs and record the deployment commit hash. | ☐
13 | 2026-09-06 | Local QA and Deploy | Optional | Ask one trusted person to test the site without explanation. | ☐
14 | 2026-09-07 | Week 2 Review | Must do | Confirm all three articles are public. | ☐
14 | 2026-09-07 | Week 2 Review | Must do | Confirm analytics test data and product-click tracking are visible. | ☐
14 | 2026-09-07 | Week 2 Review | Must do | Update the dashboard baseline. | ☐
14 | 2026-09-07 | Week 2 Review | Must do | Record unresolved blockers. | ☐
14 | 2026-09-07 | Week 2 Review | Should do | Select the first 15-20 Pin topics and create a Pin-to-article mapping. | ☐
14 | 2026-09-07 | Week 2 Review | Optional | Capture a baseline analytics screenshot. | ☐
15 | 2026-09-08 | Pin Batch One | Must do | Create five Pins for Article One. | ☐
15 | 2026-09-08 | Pin Batch One | Must do | Give each Pin a unique title, visual angle, and UTM value. | ☐
15 | 2026-09-08 | Pin Batch One | Must do | Record each Pin in the campaign tracker. | ☐
15 | 2026-09-08 | Pin Batch One | Should do | Use concrete promises and check every destination URL. | ☐
15 | 2026-09-08 | Pin Batch One | Optional | Prepare alternate descriptions. | ☐
16 | 2026-09-09 | Pin Batch Two | Must do | Create five Pins for Article Two. | ☐
16 | 2026-09-09 | Pin Batch Two | Must do | Record all metadata in the campaign tracker. | ☐
16 | 2026-09-09 | Pin Batch Two | Must do | Verify UTM links. | ☐
16 | 2026-09-09 | Pin Batch Two | Should do | Include one budget angle and one use-case angle. | ☐
16 | 2026-09-09 | Pin Batch Two | Optional | Create one comparison-style visual. | ☐
17 | 2026-09-10 | Pin Batch Three | Must do | Create five Pins for Article Three. | ☐
17 | 2026-09-10 | Pin Batch Three | Must do | Record all metadata in the campaign tracker. | ☐
17 | 2026-09-10 | Pin Batch Three | Must do | Verify that every Pin fulfills its article promise. | ☐
17 | 2026-09-10 | Pin Batch Three | Should do | Include a tiny-home or small-space angle. | ☐
17 | 2026-09-10 | Pin Batch Three | Optional | Prepare five additional variations. | ☐
18 | 2026-09-11 | Publish and Schedule | Must do | Publish or schedule the first 15 Pins. | ☐
18 | 2026-09-11 | Publish and Schedule | Must do | Start with the Future Living / Off-grid Tech board. | ☐
18 | 2026-09-11 | Publish and Schedule | Must do | Record actual publish times. | ☐
18 | 2026-09-11 | Publish and Schedule | Must do | Confirm Pinterest links resolve correctly. | ☐
18 | 2026-09-11 | Publish and Schedule | Should do | Add up to five additional Pins if quality remains high. | ☐
18 | 2026-09-11 | Publish and Schedule | Optional | Prepare a second relevant board only if the destination remains clear. | ☐
19 | 2026-09-12 | First Measurement Check | Must do | Record Pinterest impressions, Pin clicks, outbound clicks, and saves. | ☐
19 | 2026-09-12 | First Measurement Check | Must do | Record website sessions and article views. | ☐
19 | 2026-09-12 | First Measurement Check | Must do | Check product-click and affiliate-redirect events. | ☐
19 | 2026-09-12 | First Measurement Check | Must do | Fix broken links or missing UTM values. | ☐
19 | 2026-09-12 | First Measurement Check | Should do | Identify the strongest and weakest Pin promise. | ☐
19 | 2026-09-12 | First Measurement Check | Optional | Make one small landing-page improvement. | ☐
20 | 2026-09-13 | Content and Funnel Review | Must do | Compare Pin performance by title angle. | ☐
20 | 2026-09-13 | Content and Funnel Review | Must do | Compare traffic by article. | ☐
20 | 2026-09-13 | Content and Funnel Review | Must do | Check whether visitors reach product cards. | ☐
20 | 2026-09-13 | Content and Funnel Review | Must do | Record findings in the dashboard. | ☐
20 | 2026-09-13 | Content and Funnel Review | Should do | Improve one weak article section or product-card explanation. | ☐
20 | 2026-09-13 | Content and Funnel Review | Optional | Create two replacement Pins for the weakest angle. | ☐
21 | 2026-09-14 | Week 3 Review | Must do | Confirm all published Pins and website events are tracked. | ☐
21 | 2026-09-14 | Week 3 Review | Must do | Update the campaign and affiliate trackers. | ☐
21 | 2026-09-14 | Week 3 Review | Must do | Record cumulative sessions and product clicks. | ☐
21 | 2026-09-14 | Week 3 Review | Should do | Decide whether one controlled improvement is justified. | ☐
21 | 2026-09-14 | Week 3 Review | Optional | Publish replacement Pins if evidence supports them. | ☐
22 | 2026-09-15 | Affiliate Follow-up | Must do | Check responses from Impact, Awin, and direct merchants. | ☐
22 | 2026-09-15 | Affiliate Follow-up | Must do | Follow up where applications allow it. | ☐
22 | 2026-09-15 | Affiliate Follow-up | Must do | Confirm payout and Sri Lanka restrictions. | ☐
22 | 2026-09-15 | Affiliate Follow-up | Must do | Update program status and dates. | ☐
22 | 2026-09-15 | Affiliate Follow-up | Should do | Replace unusable programs with verified alternatives. | ☐
22 | 2026-09-15 | Affiliate Follow-up | Optional | Contact one relevant merchant directly. | ☐
23 | 2026-09-16 | Analytics Quality Review | Must do | Compare Pinterest outbound clicks with attributed website sessions. | ☐
23 | 2026-09-16 | Analytics Quality Review | Must do | Check UTM campaign and content values. | ☐
23 | 2026-09-16 | Analytics Quality Review | Must do | Check for attribution problems. | ☐
23 | 2026-09-16 | Analytics Quality Review | Must do | Confirm product-click events are not duplicated. | ☐
23 | 2026-09-16 | Analytics Quality Review | Must do | Record known data limitations. | ☐
23 | 2026-09-16 | Analytics Quality Review | Should do | Add notes for Pinterest estimates or delayed reporting. | ☐
23 | 2026-09-16 | Analytics Quality Review | Optional | Create a simple chart from dashboard data. | ☐
24 | 2026-09-17 | Conversion Improvement | Must do | Choose one bottleneck: Pin click, article engagement, or product click. | ☐
24 | 2026-09-17 | Conversion Improvement | Must do | Make one focused change. | ☐
24 | 2026-09-17 | Conversion Improvement | Must do | Record the change and expected effect. | ☐
24 | 2026-09-17 | Conversion Improvement | Should do | Improve one product-card CTA or comparison section. | ☐
24 | 2026-09-17 | Conversion Improvement | Optional | Create one new Pin based on the strongest topic. | ☐
25 | 2026-09-18 | Revenue and Economics Review | Must do | Record affiliate clicks, conversions, and revenue. | ☐
25 | 2026-09-18 | Revenue and Economics Review | Must do | Distinguish zero sales from missing tracking. | ☐
25 | 2026-09-18 | Revenue and Economics Review | Must do | Compare actual traffic with the conservative scenario. | ☐
25 | 2026-09-18 | Revenue and Economics Review | Must do | Record estimated weekly maintenance time. | ☐
25 | 2026-09-18 | Revenue and Economics Review | Should do | Estimate revenue per 1,000 Pinterest-attributed sessions. | ☐
25 | 2026-09-18 | Revenue and Economics Review | Optional | Identify one higher-value category worth testing later. | ☐
26 | 2026-09-19 | Audience and Content Decision | Must do | Rank articles by Pinterest sessions. | ☐
26 | 2026-09-19 | Audience and Content Decision | Must do | Rank articles by product-click rate. | ☐
26 | 2026-09-19 | Audience and Content Decision | Must do | Rank Pin angles by outbound-click rate. | ☐
26 | 2026-09-19 | Audience and Content Decision | Must do | Identify the strongest and weakest topics. | ☐
26 | 2026-09-19 | Audience and Content Decision | Should do | Write three lessons about audience intent. | ☐
26 | 2026-09-19 | Audience and Content Decision | Optional | Draft five follow-up article ideas. | ☐
27 | 2026-09-20 | Final Data Capture | Must do | Export or record the final Pinterest date range. | ☐
27 | 2026-09-20 | Final Data Capture | Must do | Record sessions, article views, product clicks, redirects, and revenue. | ☐
27 | 2026-09-20 | Final Data Capture | Must do | Update every campaign-tracker row with available data. | ☐
27 | 2026-09-20 | Final Data Capture | Must do | Update the validation dashboard. | ☐
27 | 2026-09-20 | Final Data Capture | Should do | Save screenshots or exports needed to explain the result. | ☐
27 | 2026-09-20 | Final Data Capture | Optional | Clean up duplicate or incomplete tracker rows. | ☐
28 | 2026-09-21 | Draft the Decision | Must do | Compare results with the traffic, intent, and affiliate thresholds. | ☐
28 | 2026-09-21 | Draft the Decision | Must do | Write evidence for and against continuing. | ☐
28 | 2026-09-21 | Draft the Decision | Must do | Select continue and expand, continue but reposition, or pause and stop. | ☐
28 | 2026-09-21 | Draft the Decision | Should do | Estimate the next 30-day workload and identify the biggest unresolved risk. | ☐
28 | 2026-09-21 | Draft the Decision | Optional | Ask for a second opinion. | ☐
29 | 2026-09-22 | Final Review | Must do | Recheck dashboard arithmetic. | ☐
29 | 2026-09-22 | Final Review | Must do | Confirm affiliate status evidence. | ☐
29 | 2026-09-22 | Final Review | Must do | Confirm the decision uses attributable traffic, not impressions alone. | ☐
29 | 2026-09-22 | Final Review | Must do | Confirm the next scope fits 10 hours per week. | ☐
29 | 2026-09-22 | Final Review | Should do | Write the top three lessons in plain language. | ☐
29 | 2026-09-22 | Final Review | Optional | Archive unused drafts without deleting source data. | ☐
30 | 2026-09-23 | Close the Experiment | Must do | Complete the validation dashboard. | ☐
30 | 2026-09-23 | Close the Experiment | Must do | Finalize the one-page decision memo. | ☐
30 | 2026-09-23 | Close the Experiment | Must do | Record the next 30-day scope only if evidence supports continuing. | ☐
30 | 2026-09-23 | Close the Experiment | Must do | Commit and push project, tracker, and documentation changes. | ☐
30 | 2026-09-23 | Close the Experiment | Must do | Note the date of the next review. | ☐
30 | 2026-09-23 | Close the Experiment | Should do | Update the weekly plan with approved changes. | ☐
30 | 2026-09-23 | Close the Experiment | Optional | Create the next daily plan only after the decision is approved. | ☐

## Instructions
How to Use This Workbook
1 | Open the Tasks sheet and use the Done dropdown for each task.
2 | Choose ☐ for incomplete or ☑ for complete.
3 | Add blockers, links, or evidence in the Notes column.
4 | The Dashboard updates when Excel recalculates formulas.
5 | Filter Tasks by day, focus, or priority when planning a work block.
6 | Regenerate the workbook after changing the source CSV; manual checkbox progress will not be preserved.